## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the proces and include a detailed description of every step. Add reasoning on why you took certain descisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description
Models | 1 | 2021-05-24 | Implemented initial version of the models
Migrations | 1 | 2021-05-24 | Implemented migrations
DB-Seeder | 2 | 24.05.2021-30.05.2021 | The DB-Seeder phase took longer than expected, as Phalcon, unlike Laravel, does not include the Faker library, or at least it is harder to implement as a PHP library. Therefore, after hours of research, testing with different libraries that pretended to adapt Laravel's dev tools to Phalcon, I found a JavaScript tool that took use of Faker to seed the database. Afterwards, implementing database seeding into the project was easy and did not take more than half an hour.
API-Controllers | 6 | 26.04.2021 - 29.05.2021 | Implemented api-controllers for houses, houses_filters, rooms, listings and users. Added all CRUD functionalities, JSON return types as requested in the document from DTT.
Models Advanced | 1 | 2021-05-26 | After some more research on Phalcon's documentation I have improved my models to perform checks of the inputted data. (check for null values, check for types - such as numbers, emails, unique values, etc.)
Research on Phalcon | 10 | 24.05.2021 - 30.05.2021 | Phalcon was a new PHP Framework to work with for me. I have spent many hours going through the documentation to know exactly how components should be setup to work properly.
Database setup | 1 | 2021-05-24 | Database setup on MySQL server, hosted with XAMPP
Database planning | 1 | 2021-05-24 | Reading of requirements and user stories, paper planning the database tables, structure, needed requests.
Total amount of hours | 23